## Sheet1
Sr. No. | Task Name | Duration | Start | Finish | Predecessors | Resource Names | Status
1 | SavvyShopper | 105.25 days | Wed 27-01-16 | Thu 23-06-16
2 | Requirements Analysis and Design - Phase I | 24.5 days | Wed 27-01-16 | Tue 01-03-16
3 | Savvy Shopper logo design | 4 days | Wed 27-01-16 | Mon 01-02-16 |  | UI Designer | Done
4 | Defining the system workflow definitions for each screen (data flow, screen validations) | 4 days | Tue 02-02-16 | Fri 05-02-16 | 3 | PM,Team | Done
5 | Defining the technical architecture of the search algorithms (3 days per algorithm) Optimized database design | 9 days | Mon 08-02-16 | Thu 18-02-16 | 4 | PM,Team | Done
6 | Amazon multiple brand search | 4 hrs | Fri 19-02-16 | Fri 19-02-16 | 5 | Team | Done
7 | Screen designs of the Android app with all the essential features covered | 6 days | Fri 19-02-16 | Mon 29-02-16 | 6 | UI Designer | Done
8 | Revisions to the screens as per client suggestions | 1 day | Mon 29-02-16 | Tue 01-03-16 | 7 | UI Designer | Done
9 | Development | 80.75 days | Tue 01-03-16 | Thu 23-06-16
10 | Search algorithms | 21 days | Tue 01-03-16 | Thu 31-03-16
11 | Amazon "price not found" analysis. Testing with sample data. | 2 days | Tue 01-03-16 | Thu 03-03-16 | 8 | Web Developer | Done
12 | Amazon search algorithm | 4 days | Thu 03-03-16 | Wed 09-03-16 | 11 | Web Developer | Done
13 | Bulk testing with at least 50 search criteria | 2 days | Wed 09-03-16 | Fri 11-03-16 | 12 | Web Developer | Done
14 | FlipKart search algorithm | 4 days | Fri 11-03-16 | Thu 17-03-16 | 13 | Web Developer | Done
15 | Bulk testing with at least 50 search criteria | 2 days | Thu 17-03-16 | Mon 21-03-16 | 14 | Web Developer | Done
16 | Snapdeal gather data | 1 day | Mon 21-03-16 | Tue 22-03-16 | 15 | Web Developer | Done
17 | Snapdeal search algorithm | 4 days | Tue 22-03-16 | Tue 29-03-16 | 16 | Web Developer | Done
18 | Bulk testing with at least 50 search criteria | 2 days | Tue 29-03-16 | Thu 31-03-16 | 17 | Web Developer | Done
19 | Web Services development | 18 days | Mon 04-04-16 | Wed 27-04-16
20 | Implementation of the 16 documented web services | 2 days | Mon 04-04-16 | Tue 05-04-16 |  | Web Developer | Done
21 | Fine tuning of the search algorithms: | 4 days | Wed 06-04-16 | Mon 11-04-16 | 20 | Web Developer | Done
22 | Continued Implementation of the 16 documented web services | 10 days | Tue 12-04-16 | Mon 25-04-16 | 21 | Web Developer | Done
23 | Testing and fixes | 2 days | Tue 26-04-16 | Wed 27-04-16 | 22 | Web Developer | Done
24 | Cron jobs | 11 days | Thu 28-04-16 | Thu 12-05-16
25 | Cron for email verification notification | 1 day | Thu 28-04-16 | Thu 28-04-16 | 23 | Web Developer | Done
26 | Cron to send search notifications to user | 3 days | Fri 29-04-16 | Tue 03-05-16 | 25 | Web Developer | Done
27 | Cron to send price changed notifications to user | 1 day | Wed 04-05-16 | Wed 04-05-16 | 26 | Web Developer | Done
28 | Web service enhancements for immediate search results | 6.5 hrs | Thu 05-05-16 | Thu 05-05-16 | 27 | Web Developer | Done
29 | Cron job to download latest SnapDeal file hourly | 1.5 hrs | Thu 05-05-16 | Thu 05-05-16 | 28 | Web Developer | Done
30 | Cron for Email verification not completed – block account | 2 hrs | Fri 06-05-16 | Fri 06-05-16 | 29 | Web Developer | Done
31 | Cron to fetch the Deals of the Day - Amazon | 1.5 days | Fri 06-05-16 | Mon 09-05-16 | 30 | Web Developer | Done
32 | Cron to fetch the Deals of the Day - FlipKart | 1.5 days | Mon 09-05-16 | Wed 11-05-16 | 31 | Web Developer | Done
33 | Cron to fetch the Deals of the Day - SnapDeal | 10 hrs | Wed 11-05-16 | Thu 12-05-16 | 32 | Web Developer | Done
34 | Cron to delete all searched data for inactive searches | 2 hrs | Thu 12-05-16 | Thu 12-05-16 | 33 | Web Developer | Done
35 | Cron to delete all searched data for a deleted search request | 2 hrs | Thu 12-05-16 | Thu 12-05-16 | 34 | Web Developer | Done
36 | Web Integration testing | 8 days | Fri 13-05-16 | Tue 24-05-16
37 | Testing of the backend and the web services | 4 days | Fri 13-05-16 | Wed 18-05-16 | 35 | Web Developer | Done
38 | FlipKart New API Integration | 4 days | Thu 19-05-16 | Tue 24-05-16 | 37 | Web Developer | WIP
39 | Fine tuning of the search algorithms (as required) | 3 days | Wed 25-05-16 | Fri 27-05-16 | 38 | Web Developer | Pending
40 | Android development | 39.25 days | Tue 29-03-16 | Mon 23-05-16
41 | Splash screen | 0.5 days | Tue 29-03-16 | Tue 29-03-16 |  | Android Developer | Done
42 | Sign up/Sign in | 2 days | Tue 29-03-16 | Thu 31-03-16 | 40 | Android Developer | Done
43 | Navigation Menu | 1 day | Thu 31-03-16 | Fri 01-04-16 | 41 | Android Developer | Done
44 | Home Screen | 3 days | Fri 01-04-16 | Wed 06-04-16 | 42 | Android Developer | Done
45 | Display the popuplar brands within each category (animation effect) | 3 days | Wed 06-04-16 | Mon 11-04-16 | 43 | Android Developer | Done
46 | Create New Search (4 categories) | 6 days | Mon 11-04-16 | Tue 19-04-16 | 44 | Android Developer | Done
47 | My Searches | 2 days | Tue 19-04-16 | Thu 21-04-16 | 45 | Android Developer | Done
48 | Email verification | 1.5 days | Thu 21-04-16 | Fri 22-04-16 | 46 | Android Developer | Done
49 | Handling push notifications (email not verified) | 1.5 days | Mon 25-04-16 | Tue 26-04-16 | 47 | Android Developer | Done
50 | Clicking on Buy button from anywhere in the app | 2 days | Tue 26-04-16 | Thu 28-04-16 | 48 | Android Developer | Done
51 | Milestone 1 delivery | 1 day | Thu 28-04-16 | Fri 29-04-16 | 49 | Android Developer | Done
52 | Search Results | 3 days | Fri 29-04-16 | Wed 04-05-16 | 50 | Android Developer | Done
53 | Change in colors on the home screen (brighter colors) | 2 hrs | Wed 04-05-16 | Wed 04-05-16 | 51 | Android Developer | Done
54 | Interim delivery delivery with all feedback points resolved and tasks 51, 52 | 4 hrs | Wed 04-05-16 | Thu 05-05-16 | 52 | Android Developer | Done
55 | View More Results – Tracking | 1 day | Thu 05-05-16 | Fri 06-05-16 | 53 | Android Developer | Done
56 | Immediate search results for better user experience | 3 days | Fri 06-05-16 | Wed 11-05-16 | 54 | Android Developer | Done
57 | Handling push notifications (new search results) | 1.5 days | Wed 11-05-16 | Thu 12-05-16 | 55 | Android Developer | Done
58 | Handling push notifications (price changed) | 0.5 days | Thu 12-05-16 | Fri 13-05-16 | 56 | Android Developer | Done
59 | My Savvy Deals | 2 days | Fri 13-05-16 | Tue 17-05-16 | 57 | Android Developer | Done
60 | Rate the app | 1 day | Tue 17-05-16 | Wed 18-05-16 | 58 | Android Developer | Done
61 | Send Feedback | 1 day | Wed 18-05-16 | Thu 19-05-16 | 59 | Android Developer | Done
62 | Realtime check for user account deletion | 2 days | Thu 19-05-16 | Mon 23-05-16 | 60 | Android Developer | Done
63 | Integration testing | 7 days | Mon 23-05-16 | Wed 01-06-16
64 | Testing of the backend and the Apps - Milestone 2 delivery | 7 days | Mon 23-05-16 | Wed 01-06-16 | 61 | Android Developer | Done
65 | Submission to play store | 1 day | Wed 01-06-16 | Thu 02-06-16 | 62 | Android Developer | Pending. We have prepared the graphics required for submission.
66 | UAT Support | 15 days | Thu 02-06-16 | Thu 23-06-16 | 64 | Android Developer | Pending
| Balance remaining (from 2-Jun to 23-Jun): 16x8 = 128 man hours | 128
Additional tasks done after 1-Jun-2016
1 | Preparing the graphics required for submission and signing the app | 6
2 | Identified and fixed the push notifications issue | 7
3 | Replaced the email settings (as per the new SMTP settings provided by Balaji) on all instances | 1
4 | Assisting Satyen in deployment of the code in his development environment | 1
5 | Designing the SavvyShopper 3 step tutorial | 8
6 | Tutorial Integration | 32
7 | Google ads integration | 32
8 | Renamed Mobiles to Mobile & Electronics (Category name change) | 2
9 | Setup of Facebook app, Google App for push notifications and Ad mobs. Testing with new accounts | 6
10 | Preparation of the draft listing on Google Play Store | 2
11 | Setup and testing of all CRON Jobs on PROD. QA final round of testing | 6
12 | Clean up all the data on PROD from MySQL and Mongo. | 0.5
13 | Snapdeal is disabled till the FTP issue is solved. Accordingly modified the tutorial to hide SD reference | 0.5
14 | Live build, go live readme, final check on the checklist, compiling the binary and submission on play store. | 1
15 | Password protection for accessing admin mongo interface | 1
16 | Cron job to send registration stats once in 3 days. Deployment and testing | 3.5
17 | Retest of the sign up process, increase activation window from 3 to 14, resolved the permission issue of instant sign up. | 1
18 | Released a new version of the SavvyShopper app on the play store, which will enable the deep linking i.e. when someone browses the website from mobile and clicks on download button, and if the app is already installed on the device, it will prompt to open up the SavvyShopper app directly. | 2
19 | The FlipKart API had changed slightly and therefore the results from FlipKart were not being shown in the app for all cases. E.g.: in the SavvyShopper app if you searched for “nail polish” the results were not being returned | 4
20 | Re-check on SanpDeal API technical feasibility | 1.5
21 | Enable SnapDeal in the tutorial of SavvyShopper App. Publish on play store. Also disabled the cron to delete the user account if the email has not been verified. | 1
| Total hours spent | 119
| Total hours balance | 9 | 1.125