## Sheet1
Sr. NO | Task Name | Duration | Start | Finish | Predecessors | Resource Names | Status
1 | SavvyShopper | 101.5 days | Wed 27-01-16 | Fri 17-06-16
2 | Requirements Analysis and Design - Phase I | 24.5 days | Wed 27-01-16 | Tue 01-03-16
3 | Savvy Shopper logo design | 4 days | Wed 27-01-16 | Mon 01-02-16 |  | UI Designer | Done
4 | Defining the system workflow definitions for each screen (data flow, screen validations) | 4 days | Tue 02-02-16 | Fri 05-02-16 | 3 | PM,Team | Done
5 | Defining the technical architecture of the search algorithms (3 days per algorithm) Optimized database design | 9 days | Mon 08-02-16 | Thu 18-02-16 | 4 | PM,Team | Done
6 | Amazon multiple brand search | 4 hrs | Fri 19-02-16 | Fri 19-02-16 | 5 | Team | Done
7 | Screen designs of the Android app with all the essential features covered | 6 days | Fri 19-02-16 | Mon 29-02-16 | 6 | UI Designer | Done
8 | Revisions to the screens as per client suggestions | 1 day | Mon 29-02-16 | Tue 01-03-16 | 7 | UI Designer | Done
9 | Development | 77 days | Tue 01-03-16 | Fri 17-06-16
10 | Search algorithms | 21 days | Tue 01-03-16 | Thu 31-03-16
11 | Amazon "price not found" analysis. Testing with sample data. | 2 days | Tue 01-03-16 | Thu 03-03-16 | 8 | Web Developer | Done
12 | Amazon search algorithm | 4 days | Thu 03-03-16 | Wed 09-03-16 | 11 | Web Developer | Done
13 | Bulk testing with at least 50 search criteria | 2 days | Wed 09-03-16 | Fri 11-03-16 | 12 | Web Developer | Done
14 | FlipKart search algorithm | 4 days | Fri 11-03-16 | Thu 17-03-16 | 13 | Web Developer | Done. Delay of 1 day because we need to parse the color and size variations returned by FlipKart
15 | Bulk testing with at least 50 search criteria | 2 days | Thu 17-03-16 | Mon 21-03-16 | 14 | Web Developer | Done
16 | Snapdeal gather data | 1 day | Mon 21-03-16 | Tue 22-03-16 | 15 | Web Developer | Done
17 | Snapdeal search algorithm | 4 days | Tue 22-03-16 | Tue 29-03-16 | 16 | Web Developer | Done
18 | Bulk testing with at least 50 search criteria | 2 days | Tue 29-03-16 | Thu 31-03-16 | 17 | Web Developer | Done
19 | Web Services development | 18 days | Mon 04-04-16 | Wed 27-04-16
20 | Implementation of the 16 documented web services | 2 days | Mon 04-04-16 | Tue 05-04-16 |  | Web Developer | Done
21 | Fine tuning of the search algorithms: Email dated 7th April 2016 | 4 days | Wed 06-04-16 | Mon 11-04-16 | 20 | Web Developer | Done
22 | Continued Implementation of the 16 documented web services | 10 days | Tue 12-04-16 | Mon 25-04-16 | 21 | Web Developer | Done
23 | Testing and fixes | 2 days | Tue 26-04-16 | Wed 27-04-16 | 22 | Web Developer | Done
24 | Cron jobs | 10 days | Thu 28-04-16 | Wed 11-05-16
25 | Cron for email verification notification | 1 day | Thu 28-04-16 | Thu 28-04-16 | 23 | Web Developer | Done
26 | Cron to send search notifications to user | 3 days | Fri 29-04-16 | Tue 03-05-16 | 25 | Web Developer | WIP
27 | Cron to send price changed notifications to user | 1 day | Wed 04-05-16 | Wed 04-05-16 | 26 | Web Developer | Pending
28 | Cron for Email verification not completed – block account | 2 hrs | Thu 05-05-16 | Thu 05-05-16 | 27 | Web Developer | Pending
29 | Cron to fetch the Deals of the Day - Amazon | 1.5 days | Thu 05-05-16 | Fri 06-05-16 | 28 | Web Developer | Pending
30 | Cron to fetch the Deals of the Day - FlipKart | 1.5 days | Fri 06-05-16 | Tue 10-05-16 | 29 | Web Developer | Pending
31 | Cron to fetch the Deals of the Day - SnapDeal | 10 hrs | Tue 10-05-16 | Wed 11-05-16 | 30 | Web Developer | Pending
32 | Cron to delete all searched data for inactive searches | 2 hrs | Wed 11-05-16 | Wed 11-05-16 | 31 | Web Developer
33 | Cron to delete all searched data for a deleted search request | 2 hrs | Wed 11-05-16 | Wed 11-05-16 | 32 | Web Developer | Pending
34 | Web Integration testing | 8 days | Thu 12-05-16 | Mon 23-05-16 |  |  | Pending
35 | Testing of the backend and the web services | 4 days | Thu 12-05-16 | Tue 17-05-16 | 33 | Web Developer
36 | Fine tuning of the search algorithms (as required) | 4 days | Wed 18-05-16 | Mon 23-05-16 | 35 | Web Developer | Done
37 | Android development | 35.5 days | Tue 29-03-16 | Tue 17-05-16 |  |  | Done
38 | Splash screen | 0.5 days | Tue 29-03-16 | Tue 29-03-16 |  | Android Developer | Done
39 | Sign up/Sign in | 2 days | Tue 29-03-16 | Thu 31-03-16 | 38 | Android Developer | Done
40 | Navigation Menu | 1 day | Thu 31-03-16 | Fri 01-04-16 | 39 | Android Developer | Done
41 | Home Screen | 3 days | Fri 01-04-16 | Wed 06-04-16 | 40 | Android Developer | Done
42 | Display the popuplar brands within each category (animation effect) | 3 days | Wed 06-04-16 | Mon 11-04-16 | 41 | Android Developer | Done
43 | Create New Search (4 categories) | 6 days | Mon 11-04-16 | Tue 19-04-16 | 42 | Android Developer | Done
44 | My Searches | 2 days | Tue 19-04-16 | Thu 21-04-16 | 43 | Android Developer | Done
45 | Email verification | 1.5 days | Thu 21-04-16 | Fri 22-04-16 | 44 | Android Developer | Done
46 | Handling push notifications (email not verified) | 1.5 days | Mon 25-04-16 | Tue 26-04-16 | 45 | Android Developer | Done
47 | Clicking on Buy button from anywhere in the app | 2 days | Tue 26-04-16 | Thu 28-04-16 | 46 | Android Developer | Done
48 | Milestone 1 delivery | 1 day | Thu 28-04-16 | Fri 29-04-16 | 47 | Android Developer | Done
49 | Search Results | 3 days | Fri 29-04-16 | Wed 04-05-16 | 48 | Android Developer | WIP
50 | View More Results – Tracking | 1 day | Wed 04-05-16 | Thu 05-05-16 | 49 | Android Developer | Pending
51 | Handling push notifications (new search results) | 1.5 days | Thu 05-05-16 | Fri 06-05-16 | 50 | Android Developer | Pending
52 | Handling push notifications (price changed) | 0.5 days | Mon 09-05-16 | Mon 09-05-16 | 51 | Android Developer | Pending
53 | My Savvy Deals | 2 days | Mon 09-05-16 | Wed 11-05-16 | 52 | Android Developer | Pending
54 | Rate the app | 1 day | Wed 11-05-16 | Thu 12-05-16 | 53 | Android Developer | Pending
55 | Send Feedback | 1 day | Thu 12-05-16 | Fri 13-05-16 | 54 | Android Developer | Pending
56 | Realtime check for user account deletion | 2 days | Fri 13-05-16 | Tue 17-05-16 | 55 | Android Developer | Pending
57 | Integration testing | 7 days | Tue 17-05-16 | Thu 26-05-16
58 | Testing of the backend and the Apps - Milestone 2 delivery | 7 days | Tue 17-05-16 | Thu 26-05-16 | 56 | Android Developer | Pending
59 | Submission to play store | 1 day | Thu 26-05-16 | Fri 27-05-16 | 57 | Android Developer | Pending
60 | UAT Support | 15 days | Fri 27-05-16 | Fri 17-06-16 | 59 | Android Developer | Pending